## Look-ahead
Date | Day | Job | Element | CY | First load | Pump | Finishers needed | Laborers needed | Carpenters (form day before) | Notes
11/02 | Mon | Building 3 tilt-up | Slab pour 3, east half | 180 | 5:30a | Yes | 8 | 6 | 0 | Moved from 10/29 by GC. Steel erector cleared deck.
11/02 | Mon | Mesa clinic | Footings, lines 1-4 | 42 | 7:00a | No | 2 | 5 | 0 | Inspection 6:30a. Hold if not passed.
11/03 | Tue | Building 3 tilt-up | Form panels 7-12 | 0 |  | No | 0 | 4 | 6 | Forming only. Casting bed 2.
11/03 | Tue | Chandler parking | Spread footings, grid A | 65 | 6:00a | No | 3 | 6 | 0
11/04 | Wed | Mesa clinic | Grade beams | 58 | 6:30a | No | 3 | 6 | 0 | Toolbox talk 6:30a, silica. Sign-in sheet by noon.
11/04 | Wed | Chandler parking | Form grid B footings | 0 |  | No | 0 | 3 | 5 | Forming only.
11/05 | Thu | Building 3 tilt-up | Panel casting bed 2, panels 7-12 | 148 | 5:30a | Yes | 8 | 8 | 0 | Panels need trowel finishers until 3p.
11/05 | Thu | Chandler parking | Spread footings, grid B | 70 | 6:00a | No | 3 | 6 | 0
11/06 | Fri | Mesa clinic | Slab on grade, west | 210 | 5:00a | Yes | 9 | 7 | 0 | Pump booked. Saw cuts same day.
11/09 | Mon | Building 3 tilt-up | Form panels 13-18 | 0 |  | No | 0 | 4 | 6 | Forming only.
11/09 | Mon | Chandler parking | Grade beams, grid A-B | 120 | 6:00a | No | 5 | 7 | 0
11/10 | Tue | Mesa clinic | Slab on grade, east | 205 | 5:00a | Yes | 9 | 7 | 0 | Pump booked.
11/10 | Tue | Chandler parking | Form columns, level 1 | 0 |  | No | 0 | 4 | 7 | Column forms. Carpenters all day.
11/11 | Wed | Building 3 tilt-up | Slab pour 4, west half | 190 | 5:30a | Yes | 8 | 6 | 0 | GC confirmed working Veterans Day. Confirm with crews.
11/12 | Thu | Building 3 tilt-up | Panel casting bed 2, panels 13-18 | 152 | 5:30a | Yes | 6 | 8 | 0
11/12 | Thu | Chandler parking | Columns, level 1, first half | 48 | 7:00a | Yes | 3 | 5 | 0 | Pump for columns. Small pump.
11/13 | Fri | Mesa clinic | Sidewalks and curb | 36 | 7:00a | No | 4 | 4 | 0 | Flatwork crew.
11/16 | Mon | Chandler parking | Columns, level 1, second half | 52 | 7:00a | Yes | 3 | 5 | 0 | Small pump.
11/17 | Tue | Building 3 tilt-up | Panel erection support, closure strips | 24 | 8:00a | No | 2 | 4 | 0 | Erector on site. Two finishers only.
11/18 | Wed | Mesa clinic | Dock apron and ramps | 88 | 6:00a | No | 5 | 5 | 0 | Heavy broom finish.
11/19 | Thu | Chandler parking | Elevated deck, level 2, pour A | 260 | 4:30a | Yes | 10 | 8 | 0 | Two pumps. Night crew starts 3a for setup.
11/20 | Fri | Chandler parking | Strip and reshore | 0 |  | No | 0 | 8 | 4 | No pour.

## Roster
ID | Name | Classification | Availability notes
100 | A. Ortega | Foreman | Building 3 lead
101 | B. Nguyen | Foreman | Mesa clinic lead
102 | C. Reyes | Foreman | Chandler parking lead
103 | D. Whitfield | Foreman | Float
104 | E. Salazar | Finisher
105 | F. Okafor | Finisher
106 | G. Marsh | Finisher | PTO 11/09 to 11/13
107 | H. Delgado | Finisher
108 | I. Kowalski | Finisher | PTO 11/05
109 | J. Tran | Finisher
110 | K. Bell | Finisher
111 | L. Herrera | Finisher | PTO 11/05, 11/06
112 | M. Foster | Finisher
113 | N. Castillo | Finisher | PTO 11/04 to 11/06
114 | O. Pruitt | Finisher
115 | P. Ramos | Finisher | Light duty through 11/06, no pour work
116 | Q. Lindqvist | Finisher
117 | R. Mendez | Finisher
118 | S. Grant | Laborer
119 | T. Ibarra | Laborer
120 | U. Novak | Laborer
121 | V. Pacheco | Laborer
122 | W. Hale | Laborer | PTO 11/02
123 | X. Duran | Laborer
124 | Y. Sato | Laborer
125 | Z. Molina | Laborer
126 | A. Quinn | Laborer
127 | B. Vega | Laborer | PTO 11/16 to 11/20
128 | C. Burke | Laborer
129 | D. Ochoa | Laborer
130 | E. Lowry | Laborer
131 | F. Nunez | Laborer | New hire, started 10/26
132 | G. Pike | Laborer
133 | H. Aguilar | Laborer
134 | I. Rowe | Laborer
135 | J. Soto | Laborer
136 | K. Dunn | Form carpenter
137 | L. Cruz | Form carpenter
138 | M. Vance | Form carpenter
139 | N. Ruiz | Form carpenter | PTO 11/10
140 | O. Kemp | Form carpenter
141 | P. Lara | Form carpenter
142 | Q. Frost | Form carpenter
143 | R. Ayala | Form carpenter

## Read me
SAMPLE ONLY. Invented for the CCAZ AI at Work session. Not a real company, job, or person.
Three jobs: Building 3 tilt-up (from Session 1), Mesa clinic, Chandler parking structure.
Look-ahead covers Mon 11/2 to Fri 11/20. Roster is 44 people. Pump is rented with operator, booked 48 hours ahead.
The conflicts are on purpose. Finding them is the exercise.